## Feuil1
Assignee / Weeks | 2022-12-12 | 2023-01-03 | 2023-01-11 | 2023-01-16 | 2023-01-22
Dylan | UC2 Specification | Scrum master report | Work on UC2 diagrams in Specification document | Create a Scrum Master Excel Report | Register page logic#67
| UC2 AD |  | Scrum master report | Rework UC2 Sequence Diagrams | Login page logic#69
| UC2 SD |  |  |  | Git workflow#88
Scrum master report
Matis | UC3 Specification |  | Work on UC3 specs & diagrams in Specification document |  | UI for Register page#66
| UC3 AD |  |  |  | UI for Login page#68
| UC3 SD |  |  |  | Update Spécification document UC3#93
PA | UC4 Specification | Product backlog report | Work on specification document | Create a Product Owner Excel Report | User model#75
| UC4 AD | Domain class diagram | Create task on development & non development board | Add exceptions for UC1 Sequence Diagrams | User authentication#65
| UC4 SD |  |  |  | User authentication testing#89
| UC1 Specification |  |  |  | ReWork on the Activity Diagram for the UC#94
| UC1 AD |  |  |  | Testing procedure document#87
UC1 SD
Product backlog report
All | Specification document | Specification document | Specification document
Create development board
Create non development board
Use case
| UC 1 | UC Register / Login / Logout
| UC 2 | UC Health Data
| UC 3 | UC Handle Personal Circle
| UC 4 | UC Handle Feeling Form
| UC 5 | UC Insert Data